## Vishnu
Task / Deliverable | Due Date | Status | Notes / Verification | Reviced target date | Problem statement | Solution | 17.10.2026(NEXT POINT OF ACTION)
Vaiyampalayam Furnace SQF | 15/10 | In-Progress |  | 2026-10-17
Pongaluru Press – coil issue | 14/10 | In-Progress | Under SAP testing - plant need to complete testing and provide feedback post needback changes need to be made in first stage entry BAPI | 2026-10-20
Annur payment | 2026-10-13 | In-Progress |  | 2026-10-20
Annur Maestro in PRISM | 15/10 | In-Progress | Stroke Count completed, Reports need to be added once KG conversion is completed as work order wise. | 2026-11-03
Consolidated dashboard | 12/10 | Not Started | Dashboard for project review and not for MAESTRO | 2026-10-23
SAP review meeting with corp | 14/10 | Completed
SAP ghant chart review | 10/10 | Completed
Furnace batch validation – PGR review | 17/10 | Completed | Batch wise review done with Mr.Muthuselvan out of a single batch only 2 or 3 will be moved for sampling balance will be moved for production entry.
nagpur review | 2026-10-12 | Completed | 1 part has given live next week on 22 nd other parts will be taken to barcode. |  |  |  | Reminder mail to SAP
RFID POC (K.palayam) | 25/10 | Not Started
History card POC (PGR) | 20/10 | In-Progress | History card sent for review with Mr.Sakthivel and Mr.Mayilsamy - Awaiting for conformation email
OP Buddy POC W/O scan | 19/10 | In-Progress
AI awareness / introduction | 10/10 | Not Started |  | 2026-10-20
Weekly report standardisation | 12/10 | Completed | Red/green charge based on 10-minute time and set point |  |  |  | Template will be given by vishnu - need to use it in OTnexus application
Furnace review with Durga | 12/10, 15/10, 17/10 | In-Progress | CP data – single report - Completed (Under plant review) Red/green charge based on 10-minute time and set point - Inprogress Charge comparison based on part (furnace comparision) Single chart report on main screen History card printing (OP Buddy) Instrument calibration API to Prism trial Two report formats: history card and production report - Inprogress | 2026-10-24 |  |  | Need to discuss internally about each points and update to sujith sir.
PGR issue – route card wrong process | 13/10 | Completed |  |  |  |  | Need to Fix a template to document on each issues and its solutions
Process parameter from MTLink (kp+pp) | 20/10 | Not Started
Prism / OP Buddy overload issue validation | 15/10 | Completed | Evaluated Asked software team to change the aggrigation. aggrigation taking time to load the data need to trim the aggrigation. |  |  |  | Need to send mail to poomalai sir on data loading and transfer issue fix.
Zebra evaluation | 16/10 | In-Progress | Will bring the HHD scanner and tablet for evaluation on 23/10/2026. Need to send HHD scanner to Anr HT on 20-10-2026 | 2026-10-23
FPD 15 press WBS – quote | 16/10 | In-Progress | Quote has been shared
MOM / meeting with corp+ plant | 17/10 | In-Progress | WIP and First stage under testing with Gokul |  |  |  | MOM on Firstastage and wip discussion with SAP gokul
PGR funace completion | 2026-10-19 | In-Progress | Under development
AI response mail (input required)
PO nagpur maestro | 2026-10-16 | Completed | Under EC sign
Endbit clarity from plants | 2026-10-13 | Completed | End bit is clocked manually |  |  |  | Mail confirmation from SAP rajeshwari mam
PC requisition with boopathy sir (total plants)
MD dashboard work should assigned to MAESTRO team

## Anand
Task / Deliverable | Due Date | Status | Notes / Verification | Reviced target date | Problem statement | Solution | 17.10.2026(NEXT POINT OF ACTION)
First Feat IFA | 11/10 | Not Started |  | 2026-10-20 |  |  | Should get feedback from dhyalan
Vallam RFQ offer | 15/10 | Completed | RFQ Shared with multivista,Kuka
Nagpur RFQ + IFA | 15/10 | In-Progress | Awaiting for quotation from First Feat, Muilti vista | 2026-10-21
Helical Phase 2 RFQ | 15/10 | Completed | Sent to plant team for conformation. Post conformation need to check with sujith sir whether need go with in-house or vendor
Production report validation with Prism(OP10) | 15/10 | Not Started |  | 2026-10-20
Update format report |  | Not Started | Need to check with sujith Sir |  |  |  | Stellantis , helical line production report standardization
Innovation presentation | 17/10 | In-Progress | Working on it. Mail sent on 14-10-2026 to cobot planet for verification. Awaiting for response. | 2026-10-23 |  |  | Robotics meeting on PPT discussion
Pick to light - camera installation |  | Not Started
Ganapathy - KIT PACKING(BOM- camera)

## Dinesh
Task / Deliverable | Due Date | Status | Notes / Verification | Reviced target date | Problem statement | Solution | 17.10.2026(NEXT POINT OF ACTION)
RFQ Anand | 15/10 | In-Progress | RFQ shared with vendor for vallam, Nagpur and Helical Phase 2 Shared with plant team for confirmation | 2026-10-21 |  |  | Need to send a reminder mail(PGR jigging RFQ pending)
Helical production report | 12/10 | Not Started | Helical line cobot programming started on 16.10.2026. Cobot programming completed for 1 machine. plant team need to confirm the quality to proceed further. (Under qualityt trial) | 2026-10-30
Daimler 4-cobot | 15/10 | Completed | Diamler 4 cobot installed in line and activitied for one cell programming initiated |  |  |  | Daily production report should be sent to sujtih sir (mynthan)
Update WBS | 13/10 | In-Progress | Working on updating the wbs for each projects | 2026-10-20
Helical Phase 2 – vendor / in-house |  | In-Progress | RFQ prepared, yet to decide, Need to discuss with Sujith Sir | 20/25/29 -10-2026 |  |  | 1)Mechanical fixtures(MBD & PRIMEX), 2)Cobo design ( Robonetics) , 3)cobo input and output table(linen) 4)20- dinesh input ,5) 25 - vendor side quotatiton , 6)27 - review meeting , 7) HELICAL phase 2 simulation by sanjay
Texonics trial | 19/10 | Not Started | Texsonics trail planned for 1310 part in polaris line, P.Palayam | 2026-10-22 |  |  | Need to get quotation from vendor
Texonics PO RFQ | 15/10 | Completed | RFQ shared for 1310 part and vision inspection. | 2026-10-20 |  |  | Need to get quotation from vendor(cobo + robo) , camera demo , EOT , WBS(start to complete process with dates - MYNTHAN)
Stellantis wash | 16/10 | Completed | Ultrasonic washing full programming completed, plan to start production | 2026-10-20 |  |  | Grouting(21/10) , machine modification(20/10) , (return conveyor design discussion - TEAMS CALL ON 20/10)
RAD simulation | 15/10 | Completed | Simulation shared for RAD line that could not accomodate 6 work order
Next 5 years quantity |  | Completed | Shared through mail
Next 6 months quantity |  | In-Progress | Working with priority parts with high volume in each plants | 2026-10-20
Resource plan |  | Not Started | Need to discuss with sujith Sir
Voice-assist robot |  | Not Started | Yet to start-Discussion ongoing with mynthan. WPS need to be shared | 2026-10-23
Innovation slide presentation | 17/10 | In-Progress | Working on it. Mail sent on 14-10-2026 to cobot planet for verification. Awaiting for response. | 2026-10-23

## Durga
Task / Deliverable | Due Date | Status | Subtasks / Notes | Reviced target date | Problem statement | Solution | Priority | 17.10.2026(NEXT POINT OF ACTION)
KP OP trial machine ANDON | 10/10 | Completed(Awaiting for plant feedback) | [5 empty] | Need to get a picture of OB screen from plant side(hari balan - MD projects)
Feedback – OP Buddy | 14/10 | Completed(Awaiting for plant feedback) | Awaiting for plant feedback. Reminder emailo sent on 16-10-2026
SAP ghant chart | 11/10 | Completed
Furnace Report | 2026-10-17 | Completed | CP data – single report |  |  |  |  | Next review with furnace team
|  | Inprogress | Red/green charge based on 10-minute time and set point | 2026-10-20 |  |  |  | History card template confirmation(21/10)
|  | Not Started | Charge comparison based on part (furnace comparision) | 2026-10-24
|  | Completed | Single chart report on main screen |  |  |  | mark in red
|  | Inprogress | History card printing (OP Buddy). Awaiting for template conformation
|  | Not Started | Instrument calibration API to Prism trial. Need to plan need to arrange meeting with Mr.sakthivel sir on 20-10-2026
|  | Inprogress | Two report formats: history card and production report
Dispatch Management | 17/10 | Not Started | SRS completed got approval Mr sathish PGR.Wired frame need to be prepared. | 2026-10-25
OEE Report – Leanworx replication | 14/10 | Inprogress |  | 2026-10-23
Test all project reports | 14/10 | Not Started |  | 2026-10-24 |  |  |  | Loading issue , PDF standardization with loog's
H1 + H2 Report | 22/10 | Not Started |  | 2026-10-24
Expense-based Report | 22/10 | Not Started |  | 2026-10-24
Quality Feeder – plan live (K.palayam) | 20/10 | Not Started |  | 2026-10-17 |  |  |  | Need to send a reminder mail on quality feeder revised BAPI(17/10)
Machine Manual AI deployment in Asset + OB | 28/10 | Not Started |  | 2026-10-17 |  |  |  | Need to send mail to sujith sir on large files uplaoding issue on AI(asse)
Cobot learnings integration (Mynthan) | 20/10
CMBAF furnace template - Finalization |  |  |  | 2026-10-24
Line dashboard - KP | [6 empty] | mARK IN red

## Mynthan
S. No. | Task / Deliverable | Due Date | Status | Subtasks / Notes | Reviced target date | Problem statement | Solution | Priority | 17.10.2026(NEXT POINT OF ACTION)
1 | K.Palayam Operator block C | 2026-10-14 | Inprogress | rad part testing waiting for plant side approval .we have planned klinke and cone and Pawl parts next. Mail has been sent on 12/10/2026 to Mr.Ravikumar awaiting for conformation.Reminder mail sent on 16/10/2026 | 2026-10-22 |  |  |  | Need to send mail to ravikumar to rasie PR for additional devices in machines(produciotn)
2 | Block C 4 machine interlock | 2026-10-14 | Inprogress | Ethernet pending in 4 machines (plant team infomed by next week 23/10/2026) | 2026-10-23
3 | MBD Machine data collection | 2026-10-17 | Not started | mail has given MBD team to visit. | 2026-10-20 |  |  |  | Grinding machine
4 | Bosch data collection | 2026-10-15 | Inprogress | Total 60 machine 15 machines displying in prism balance no device and ethernet cables (mail has been given to plant side for BOM) |  |  |  |  | Qty of IOT devices list (21/10)
5 | 8 machine bosch mt link i | 2026-10-15 | Inprogress | 5 Machines completed balance 3 machines need the port access (we sent the mail to plant balce 3 machines) | 2026-10-29 |  |  |  | Need to get access from karthick sir
6 | elcon integration prism | (11/10) | Completed
7 | CMBF furnace prism | (15/10) | inprogress | 1 CMBF furnace pending need to work - Annur | 2026-10-21
8 | energy meter converter PR rs485 | (12/10) | completed | PR completed
9 | CNC PR BOM(texonics IOT device) | (14/10) | Not started | need to display the cnc machine data for 1 machine then only the BOM can be prepared | 2026-10-20
10 | CNC prism plan | (13/10) | Not started | BOM not prepared,need to display the cnc machine data for 1 machine then only the BOM can be prepared | 2026-10-20
11 | OB drawing view feedback | (14/10) | Inprogress | plant side will give the feedback by this EOM (30-10-2026) |  |  |  |  | AGIS implementation in PGR plant
12 | charge in/out | (12/10) | Inprogress | mail has given to plant team ( no response from plant side). Reminder email sent on 16-10-2026 | 2026-10-22
13 | SQF furnace(P.P) | 2026-10-10 | Completed | data has been captured in DB need to display in PRISM
14 | Elcon trial | (17/10) | Not started | wait for noufal R&D . will visit on 20/10/2026 | 2026-10-20 |  |  |  | To test in p.palayam plant
15 | dashboard Stellantis shopfloor | (15/10) | completed | [5 empty] | Robonetics scope
16 | dashboard helical shop floor | (17/10) | Inprogress | Ethernet pending (plant team infomed will be completed by next week 24/10/2026) | 2026-10-27
17 | Nagpur PR PO list | 2026-10-11 | Inprogress | veerappa boopathi sir approval pending |  |  |  |  | Need to discuss with boopathy sir for alternative PC
18 | COBOT comparision chart prism vs sap | 2026-10-15 | Completed
19 | FPD 2 plan wbs | 2026-10-14 | Inprogress | quotation shared ethernet need to install, WPS need to be shared | 2026-10-22
20 | Innovation Presentation Robotics | 2026-10-17 | Not started | Need to discuss with Dinesh
21 | Learnings Cobot | 2026-10-15 | Inprogress | Need to discuss with Dinesh
22 | rotary furnace | (19/10) | Not started | Mail has given to MBD team ( need to follow up)
23 | RS485 device(ENERGY METER) | (19/10) | inprogress | po raised device need to arrive
24 | dashboard diamler shopfloor | (19/10) | Inprogress | Ethernet pending (plant team infomed will be completed by saturday) | 2026-10-25
25 | diamler cobot prism | (19/10) | Inprogress | Ethernet pending (plant team infomed will be completed by saturday) | 2026-10-25
26 | daimler data log prism | (19/10) | Inprogress | Ethernet pending (plant team infomed will be completed by next week) | 2026-10-25
27 | Need to raise mail to plant team regarding ethernet connectivity(mynthan) - vaiyampalayam ( NEED MBD SUPPORT) | 2026-10-21
28 | RAD line dashboard - cobo | 2026-10-21
29 | ROBONETICS software UI change |  |  |  | 2026-10-17 |  |  | Mark in red | Should give inputs to vendor on Dashboard UI changes

## Naveen
S. No. | Task / Deliverable | Due Date | Status | Subtasks / Notes | Alternative date | Problem statement | Solution | Priority | 17.10.2026(NEXT POINT OF ACTION)
1 | Production entry – Cobot flow (screen) | 13/10 | Not Started | Need time will start development by 30/10/2026 | 30.10.2026 |  |  |  | Should get feedback from dhyalan
2 | Production entry – Cobot flow (deploy) | 19/10 | Not Started
3 | First-stage entry (SAP) | 20/10 | Inprogress | First stage entry completed , Feedback points need to complete
4 | Maestro – Prism reports list | 15/10 | Completed | Reports are listed in Excel with WBS
5 | Maestro + Leanworx replicator for CNC | 14/10 | Not Started |  | 2026-10-28
6 | Single-screen OP Buddy (machine-linked) | 15/10 | Completed | Integrated Single screen Operator buddy in machine
7 | P2 Light installation | 16/10 | Completed | Given Vpn Access and Controller installed in Tvs line area |  |  |  | mark in red
8 | P2 Lite hot loop | 17/10 | Not Started
9 | P2 Lite trial column | 18/10 | Not Started
10 | P2 Lite first report | 20/10 | Not Started
11 | P2L UAT report | 21/10 | Not Started
12 | Planning module (SAP) | 21/10 | Not Started | Subtasks: mail, field list, BOM list, review meeting, chart.
13 | Downtime pop-up – OP Buddy | 19/10 | Not Started
14 | Furnace dashboard | 17/10 | Inprogress
15 | CMBF input to Durga for screen |  | Not Started | Need plant team to verify - Annur
16 | MD Dashboard (Plan) | 25/10 | Not Started
17 | OT Feedback – Production Server |  | Completed | Already In Production Server
18 | Production Server movement | 2026-10-25 | Not Started | (SFQA, OB, PRISM)
19 | Maruthi completion | 17/10 | Inprogress | Application Deployed locally and needs to integrate Ai in SFQA Application. | 30.10.2026
20 | Kit Packing | 17/10 | Not Started | Camera location; camera scope + purchase; software POC; display BOM + quantity; touch/display. Trial: 20/10. Deploy and PC BOM: 25/10.Camera location need to be verified by Anand and naveen need to discuss on BOM with ranganathan sir | 23.10.2026
21 | Calibration keyence (PPalayam) | 23/10 | Not Started | Screen and live.
22 | Timing mark / tooth / furnace / SFQA – OP feedback | 2026-10-23 | Not Started
23 | Tool life plan + flow | 20/10 | Not Started
24 | SFQA PP – 38 numbers | 16/10 | Not Started | Excel file need to be prepared | 21.10.2026
25 | SFQA PP – Installation | 25/10 | Not Started
26 | Draw-in display AGIS | 25/10 | Not Started
27 | MPI Packaging | 23/10 | Not Started
28 | SMD Software | 23/10 | Inprogress
29 | Roller test plan (Mythan + Noufal) | 12/10 | Not Started | Noufal & mynthan need to verify the HMI in roller test machine | 21.10.2026
30 | FS camera – Kit Pack |  | Not Started
31 | Rad Line Dashboard | 2026-10-22 | Inprogress | Assigned the Task to Hariharan
32 | 8T press machine - Shaft linkage for 1561 Part | 2026-10-23 | Inprogress | Waiting for plant team availability
33 | Complete SSR document for kit packing with perfect plan and actual dates including software + camera integration
34 | Revised MAESTRO checklist report with planned and actual dates(WBS)

## noufal
S. No. | Task / Deliverable | Due Date | Status | Subtasks / Notes | Alternative date
1 | 3D Enclosure - IOT device & SMD | 2026-10-24 | Not Started
2 | Checklist documents (soak test , repeatability test)